Introduction to Software Engineering

Weekly Status Report

Student teams must complete the Weekly Status Report for the assigned course project, using the attached template.

Software Engineering Department

Faculty of Information Technology

University of Science

Table of Contents

Objectives	1

1	Submission	1

2	Report Information	1

2.1	Work Status	1

2.2	Next Week's Plan	1

2.3	Issues and Risks	1

2.4	Meeting Minutes	1

2.5	Metrics	1

Weekly Status Report

# Objectives

This document focuses on the following:

- Report weekly progress against the project plan

- Record issues and risks

- Document the weekly status meeting

# Submission

- Submit one report per week, from week 2 to week 10 (9 reports in total). The team leader (or the backup) is responsible.

- Each team chooses its own weekly deadline (e.g., the day after the status meeting) and states it clearly in PA1.

- Commit the report to the repository at: /docs/management/weekly/W<week>-status.docx (or .md), e.g., W03-status.docx. Do not overwrite or rewrite previous reports; the commit history is evidence of on-time submission.

- Reports are not submitted on Moodle. They are graded at the end of the course under the Teamwork and Tool Usage (workflow) component.

# Report Information

| Item | Value |
| --- | --- |
| Team | T04 |
| Week | 2 |
| Meeting date | 25 Oct 2026 |
| Current phase / PA | PA2 – Software Requirements Specification (SRS) |
| Prepared by | Nguyễn Minh Trí |
| Overall status | On track |

## Work Status

| WBS / Task | Owner | Planned completion | Status | % complete | Notes |
| --- | --- | --- | --- | --- | --- |
| 1.3 Research existing court booking apps (ALOBO, MeWin, Datsan247) | Whole team | Next status meeting | In progress | 30% | Carried over from week 1 (30%) |
| 2.1 Finalize the Introduction (Purpose & Scope, Glossary), Problem Statement (expanded from PA1) and Stakeholders list | Team leader | Next status meeting | In progress | 70% | Drafted from PA1; two roles only (player and operator – facility staff and operator are the same role) |
| 2.2 Specify Functional Requirements (FR by MoSCoW), Non-Functional Requirements (NFR with measurable criteria), Business Rules (BR) and Acceptance Criteria | Trí, Vĩ | Next status meeting | In progress | 50% | FR drafted from PA1 features F01–F05; booking rules agreed (30-min slot, 5-min hold, cancel ≥3 h before start, owner changes ≥24 h) |
| 2.3 Build the Use Case Diagram, Actor/Use Case list, and write detailed specifications for at least 6 key (Must-have) Use Cases | Vĩ, Khôi | Before PA2 resubmission | In progress | 70% |  |
| 2.4 Design Prototype / Mockups for the main screens (with interactive link) and build the Requirements Traceability Matrix (RTM) | Whole team | Before PA2 resubmission | In progress | 50% |  |
| 2.5 Hold a Requirements Review meeting, record issues raised and how they were resolved to finalize the baseline | Trí, Khôi | Before PA2 submission | In progress | 50% |  |
| 2.6 Compile the PA2 document, fill in the team member contribution evaluation (with commit/task evidence) and complete the AI Usage Log | Team leader | PA2 due date | Not started | 0% |  |

## Next Week's Plan

| WBS / Task | Owner | Planned completion |
| --- | --- | --- |
| 3.1 Update SRS sections 2–5 (Introduction, Problem Statement, Stakeholders, Requirements) to match the agreed PA2 team decisions and finalize them | Team leader, Trí | Next status meeting |
| 3.2 Complete the Non-Functional Requirements (measurable criteria), Business Rules and Acceptance Criteria | Trí, Vĩ | Next status meeting |
| 3.3 Build the Use Case Diagram, Actor/Use Case list, and write detailed specifications for at least 6 key (Must-have) Use Cases | Vĩ, Khôi | Before PA2 resubmission |
| 3.4 Design Prototype / Mockups for the main screens (with interactive link) and build the Requirements Traceability Matrix (RTM) | Whole team | Before PA2 resubmission |
| 3.5 Hold a Requirements Review meeting, record issues raised and how they were resolved to finalize the baseline | Trí, Khôi | Before PA2 submission |
| 3.6 Compile the PA2 document, fill in the team member contribution evaluation (with commit/task evidence) and complete the AI Usage Log | Team leader | PA2 due date |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| I-02 | Several PA2 decisions changed during team review (e.g., slot length 1 h → 30 min; booking, hold and cancellation rules), so SRS sections 2–5 no longer match the team agreement | Rework of the requirements; possible delay to PA2 | Update sections 2–5 to match the agreed decisions and re-check with the team leader | Trí | Next status meeting |

## Meeting Minutes

| Member | Present | Done since last meeting | Next steps | Blockers |
| --- | --- | --- | --- | --- |
| Bùi Nguyễn Đăng Khoa (24127421) | Yes | Compared the SRS drafts with Trí and agreed the PA2 decisions (slot length, order structure, booking and cancellation rules) Prepared the PA2 document skeleton | Review the updated sections 2–5; track PA2 progress on the task board; prepare the Requirements Review meeting | None |
| Nguyễn Minh Trí (24127569) | Yes | Drafted SRS sections 2–5 (Introduction, Problem Statement, Stakeholders, Requirements) from PA1; went through the comparison with the team leader’s version | Update sections 2–5 to match the agreed decisions; finalize the FR specification | None |
| Lý Sĩ Vĩ (24127587) | Yes | Drafted the Non-Functional Requirements, Business Rules and Acceptance Criteria | Finalize the NFR, Business Rules and Acceptance Criteria; start the Use Case specifications | None |
| Vương Gia Khôi (23127074) | Yes | Reviewed the PA2 requirements and prepared for the Use Case diagram and mockups | Build the Use Case diagram, write the Must-have Use Case specifications and design the Prototype / Mockups | None |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 0 | 2 |
| Commits | 3 | 4 |
| Pull requests merged / reviewed | 0 | 0 |
| Open bugs (PA5) | Not applicable | Not applicable |